MINUTES OF MEETING (MoM)

Meeting Title: College Event Planning Meeting

Date: 10 September 2026

Time: 11:00 AM – 12:00 PM

Venue: Seminar Hall

Chairperson: Faculty Coordinator

Attendees : Faculty Coordinator and Student Committee Members

- Purpose of the Meeting

Planning the next cultural event and assigning responsibilities to the students.

2. Points Discussed

- Determining the event date and venue.

- Cultural activities/performances to be conducted.

- Budget needed for the event.

- Arrangements of decoration and stage.

- Food and refreshments arrangements.

- Promoting the event via social media posts and posters.

- Arrangement of registration process for the participants.

3. Decisions Taken

- The event will take place at the college seminar hall.

- Different teams will be made among the students for conducting the event.

- Preparation of budget proposal will be done by the students and will be presented to the faculty coordinator.

- The publicizing team will prepare posters and social media posts.

- Online registration process will be arranged.

4. Action Items

Task| Responsible Person/Team |Deadline

Prepare budget |FinanceTeam12| Sept

Design posters   |Publicity Team| 13 Sept

Manage registrations |RegistrationTeam|15 Sept

Arrange decorations | Decoration Team|18 Sept

Coordinate performances |Cultural Team|18 Sept

5. MEMBERS PRESENT

| SR.NO | NAME | DESIGNATION |
| --- | --- | --- |
| 1 | Dr. A. Sharma | Head of Department Faculty Coordinator |
| 2 | Ms. R. Patil | Assistant Professor |
| 3 | Mr. S. Deshmukh | Assistant Professor |
| 4 | Ms. P. Joshi | Lab Coordinator |
| 5 | Mr. A. Kulkarni | Student Representative |

6. Next Meeting

Date: 19 September 2026

Time: 11:00 AM

Venue: Conference Room, Room No.430

7. CONCLUSION

Meeting concluded at: 12:00 PM

Prepared By:

PRAGATI CHAUDHARY

STUDENT

Approved By:

Ms. LABHANI RAHANGDALE

FACULTY COORDINATOR